## Gantt Chart
PROJECT: Lochinvar Fan Diagonostic Tool
Team 7 |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | 2024-08-29 |  |  |  | September | [20 empty] | October | [60 empty] | December | [43 empty] | January | [20 empty] | February | [22 empty] | March | [35 empty] | April | [28 empty] | May
Scrolling increment: | 14 | time axis 2024-09-12 to 2025-06-02
Milestone description | Category | Progress | Start | Days | time axis 2024-09-12 to 2025-06-02
Project Proposal | On Track |  | 2024-09-12 | 18
Preliminary Research | Low Risk |  | 2024-09-25 | 14
Conceptual Design Drafting | On Track |  | 2024-10-09 | 8
Fall Break | On Track |  | 2024-10-17 | 2
Conceptual Design Finalize | Low Risk |  | 2024-10-18 | 10
Subsystem Interfacing | Med Risk |  | 2024-10-21 | 14
Circuit Design | High Risk |  | 2024-10-21 | 21
PCB Design |  |  | 2024-11-10 | 21
Detailed Design | On Track |  | 2024-10-28 | 34
Final Presentation | Low Risk |  | 2024-11-17 | 14
Winter Break | On Track |  | 2024-12-12 | 35
Ordering | On Track |  | 2025-01-16 | 14
PCB Assembly | Low Risk |  | 2025-01-26 | 24
Programming Microcontrollers | On Track |  | 2025-01-26 | 30
Experimentation & analysis | Low Risk |  | 2025-02-01 | 28
Iteration and debug | On Track |  | 2025-03-01 | 60
Final report and presentation | Low Risk |  | 2025-04-01 | 30
To add more data, Insert new rows ABOVE this one